## Test Plan
# | PHASE | API | Method (Call) | Marketplace | Scope | Test Procedure | Input Datasheet name | Main Program Name (Python Script Name) | ETA | SCRIPT STATUS | Test Plan, Scenarios and Scripts Created By
1 | PHASE1 | Order API | GetOrderById | Amazon | Regression Script | 1. To insert an Order into CSO table for Amazon marketplace with all the fields. 2. To insert a row into CSO_AMAZON table for amazon marketplace with all the fields. 3. And to run the GetOrderByID call by reading the input data from the datasheet and to see if the call is success. 4. And to see if all the data (CSO fields) are fetched by the API call. 5. And then to validate each and every data and XML tags fetched by the API call (response) against the checkpoints (expected data/tags) that are available in the data sheet 6. And publish the results. (Results will be displayed in the terminal and also documented in a file ‘Test_Report’) (Note: All the input data and the expected data/tags are read from the data sheet by the script) | orderaz.csv | Order_getOrderById_AZ.pyc | 01/2020 | DONE | Salaudeen
2 | PHASE1 | Order API | GetOrderByDate | Amazon | Regression Script | 1. To insert an Order into CSO table for Amazon marketplace with all the fields. 2. To insert a row into CSO_AMAZON table for amazon marketplace with all the fields. 3. And to run the GetOrderByDate call by reading the input data from the datasheet and to see if the call is success. 4. And to see if all the data (CSO fields) are fetched by the API call. 5. And then to validate each and every data and XML tags fetched by the API call (response) against the checkpoints (expected data/tags) that are available in the data sheet 6. And publish the results. (Results will be displayed in the terminal and also documented in a file ‘Test_Report’) (Note: All the input data and the expected data/tags are read from the data sheet by the script) | orderaz.csv | Order_getOrderByDate_AZ.pyc | 02/2020 | DONE | Salaudeen
3 | PHASE1 | Order API | GetOrderByStatus | Amazon | Regression Script | 1. To insert an Order into CSO table for Amazon marketplace with all the fields. 2. To insert a row into CSO_AMAZON table for amazon marketplace with all the fields. 3. And to run the GetOrderByStatus call by reading the input data from the datasheet and to see if the call is success. 4. And to see if all the data (CSO fields) are fetched by the API call. 5. And then to validate each and every data and XML tags fetched by the API call (response) against the checkpoints (expected data/tags) that are available in the data sheet 6. And publish the results. (Results will be displayed in the terminal and also documented in a file ‘Test_Report’) (Note: All the input data and the expected data/tags are read from the data sheet by the script) | orderaz.csv | Order_getOrderByStatus_AZ.pyc | 02/2020 | DONE | Salaudeen
4 | PHASE1 | Inventory API | GetInventory | GENERIC | Regression Script | 1. To insert a product into Listing table for any marketplace with all the required fields. 2. And to run the GetInventory call by reading the input data from the datasheet and to see if the call is success. 3. And to see if all the required data (listing fields) are fetched by the API call. 4. And then to validate each and every data and XML tags fetched by the API call (response) against the checkpoints (expected data/tags) available in the data sheet 5. And publish the results. (Results will be displayed in the terminal and also documented in a file ‘Test_Report’) (Note: All the input data and the expected data/tags are read from the data sheet by the script) | inv.csv | Inventory_getInventory.pyc | 01/2020 | DONE | Salaudeen
5 | PHASE1 | Inventory API | GetSkuQuantity | GENERIC | Regression Script | 1. To insert a product into Listing table for any marketplace with all the required fields. 2. And to run the GetSkuQuantity call by reading the input data from the datasheet and to see if the call is success. 3. And to see if all the required data (listing fields) are fetched by the API call. 4. And then to validate each and every data and XML tags fetched by the API call (response) against the checkpoints (expected data/tags) available in the data sheet 5. And publish the results. (Results will be displayed in the terminal and also documented in a file ‘Test_Report’) (Note: All the input data and the expected data/tags are read from the data sheet by the script) | inv.csv | Inventory_getSkuQuantity.pyc | 02/2020 | DONE | Salaudeen

## Scenarios
Scenario # | API | Method (Call) | Scope | Input Datasheet name | Automation Scenarios | Main Program Name (Python Script Name) | Comments | Case# | Cases & Expectation | Script Execution Status | Scenarios and Scripts Created By
1 | Order API | GetOrderById | Regression Script | orderaz.csv | 1. To insert an Order into CSO table for Amazon marketplace with all the fields. 2. To insert a row into CSO_AMAZON table for amazon marketplace with all the fields. 3. And to run the GetOrderByID call by reading the input data from the datasheet and to see if the call is success. 4. And to see if all the data (CSO fields) are fetched by the API call. 5. And then to validate each and every data and XML tags fetched by the API call (response) against the checkpoints (expected data/tags) that are available in the data sheet 6. And publish the results. (Results will be displayed in the terminal and also documented in a file ‘Test_Report’) (Note: All the input data and the expected data/tags are read from the data sheet by the script) | Order_getOrderById_AZ.pyc | The data sheet ‘orderaz.csv’ can be manipulated and the script will show the results accordingly. | 1 | CASE: All the data specified in the data sheet are correct, and run the script EXPECTED: The script should perform the call and validate all the tags/data, and should publish the overall result as ‘PASSED’. Also the status code 200 should be displayed, Along with individual tag/data validation status as PASSED |  | Salaudeen
[8 empty] | 2 | CASE: Some of the field data specified in the data sheet are NOT correct, and run the script EXPECTED: The script should perform the call and validate all the tags/data, and should publish the overall result as ‘PASSED WITH ERROR / DATA MISMATCH’. Also the status code 200 should be displayed, along with the individual tag/data validation status like FAILED or PASSED |  | Salaudeen
[8 empty] | 3 | CASE: Username or password are not correct in the data sheet, and run the script EXPECTED: The scipt should perform the call, and should publish the overall result as ‘FAILED’, along with reason for failure ‘Security Error’ and the status code 500. |  | Salaudeen
[8 empty] | 4 | CASE: Endpoint is not correct in the data sheet, and run the script EXPECTED: The scipt should perform the call, and should publish the overall result as ‘FAILED’, along with reason for failure ‘No Service found. Your Endpoint could be wrong.’ and the status code 404. |  | Salaudeen
[8 empty] | 5 | CASE: Remove one or some of the data columns in the data sheet, and run the script EXPECTED: The script should perform the call and validate all the tags/data, and should publish the overall result as ‘PASSED WITH ERROR / DATA MISMATCH’. Also the status code 200 should be displayed, A warning/failed message should be displayed stating that ‘MAY BE THE COLUMN/DATA ARE MISSING IN YOUR INPUT FILE. FILL THE REQUIRED TEST DATA AND TRY AGAIN..” Along with the other individual tag/data validation status as PASSED |  | Salaudeen
2 | Order API | GetOrderByDate | Regression Script | orderaz.csv | 1. To insert an Order into CSO table for Amazon marketplace with all the fields. 2. To insert a row into CSO_AMAZON table for amazon marketplace with all the fields. 3. And to run the GetOrderByDate call by reading the input data from the datasheet and to see if the call is success. 4. And to see if all the data (CSO fields) are fetched by the API call. 5. And then to validate each and every data and XML tags fetched by the API call (response) against the checkpoints (expected data/tags) that are available in the data sheet 6. And publish the results. (Results will be displayed in the terminal and also documented in a file ‘Test_Report’) (Note: All the input data and the expected data/tags are read from the data sheet by the script) | Order_getOrderByDate_AZ.pyc | The data sheet ‘orderaz.csv’ can be manipulated and the script will show the results accordingly. | 6 | CASE: All the data specified in the data sheet are correct, and run the script EXPECTED: The script should perform the call and validate all the tags/data, and should publish the overall result as ‘PASSED’. Also the status code 200 should be displayed, Along with individual tag/data validation status as PASSED |  | Salaudeen
[8 empty] | 7 | CASE: Some of the field data specified in the data sheet are NOT correct, and run the script EXPECTED: The script should perform the call and validate all the tags/data, and should publish the overall result as ‘PASSED WITH ERROR / DATA MISMATCH’. Also the status code 200 should be displayed, along with the individual tag/data validation status like FAILED or PASSED |  | Salaudeen
[8 empty] | 8 | CASE: Username or password are not correct in the data sheet, and run the script EXPECTED: The scipt should perform the call, and should publish the overall result as ‘FAILED’, along with reason for failure ‘Security Error’ and the status code 500. |  | Salaudeen
[8 empty] | 9 | CASE: Endpoint is not correct in the data sheet, and run the script EXPECTED: The scipt should perform the call, and should publish the overall result as ‘FAILED’, along with reason for failure ‘No Service found. Your Endpoint could be wrong.’ and the status code 404. |  | Salaudeen
[8 empty] | 10 | CASE: Remove one or some of the data columns in the data sheet, and run the script EXPECTED: The script should perform the call and validate all the tags/data, and should publish the overall result as ‘PASSED WITH ERROR / DATA MISMATCH’. Also the status code 200 should be displayed, A warning/failed message should be displayed stating that ‘MAY BE THE COLUMN/DATA ARE MISSING IN YOUR INPUT FILE. FILL THE REQUIRED TEST DATA AND TRY AGAIN..” Along with the other individual tag/data validation status as PASSED |  | Salaudeen
3 | Order API | GetOrderByStatus | Regression Script | orderaz.csv | 1. To insert an Order into CSO table for Amazon marketplace with all the fields. 2. To insert a row into CSO_AMAZON table for amazon marketplace with all the fields. 3. And to run the GetOrderByStatus call by reading the input data from the datasheet and to see if the call is success. 4. And to see if all the data (CSO fields) are fetched by the API call. 5. And then to validate each and every data and XML tags fetched by the API call (response) against the checkpoints (expected data/tags) that are available in the data sheet 6. And publish the results. (Results will be displayed in the terminal and also documented in a file ‘Test_Report’) (Note: All the input data and the expected data/tags are read from the data sheet by the script) | Order_getOrderByStatus_AZ.pyc | The data sheet ‘orderaz.csv’ can be manipulated and the script will show the results accordingly. | 11 | CASE: All the data specified in the data sheet are correct, and run the script EXPECTED: The script should perform the call and validate all the tags/data, and should publish the overall result as ‘PASSED’. Also the status code 200 should be displayed, Along with individual tag/data validation status as PASSED |  | Salaudeen
[8 empty] | 12 | CASE: Some of the field data specified in the data sheet are NOT correct, and run the script EXPECTED: The script should perform the call and validate all the tags/data, and should publish the overall result as ‘PASSED WITH ERROR / DATA MISMATCH’. Also the status code 200 should be displayed, along with the individual tag/data validation status like FAILED or PASSED |  | Salaudeen
[8 empty] | 13 | CASE: Username or password are not correct in the data sheet, and run the script EXPECTED: The scipt should perform the call, and should publish the overall result as ‘FAILED’, along with reason for failure ‘Security Error’ and the status code 500. |  | Salaudeen
[8 empty] | 14 | CASE: Endpoint is not correct in the data sheet, and run the script EXPECTED: The scipt should perform the call, and should publish the overall result as ‘FAILED’, along with reason for failure ‘No Service found. Your Endpoint could be wrong.’ and the status code 404. |  | Salaudeen
[8 empty] | 15 | CASE: Remove one or some of the data columns in the data sheet, and run the script EXPECTED: The script should perform the call and validate all the tags/data, and should publish the overall result as ‘PASSED WITH ERROR / DATA MISMATCH’. Also the status code 200 should be displayed, A warning/failed message should be displayed stating that ‘MAY BE THE COLUMN/DATA ARE MISSING IN YOUR INPUT FILE. FILL THE REQUIRED TEST DATA AND TRY AGAIN..” Along with the other individual tag/data validation status as PASSED |  | Salaudeen
4 | InventoryAPI | GetInventory | Regression Script | inv.csv | 1. To insert a product into Listing table for any marketplace with all the required fields. 2. And to run the GetInventory call by reading the input data from the datasheet and to see if the call is success. 3. And to see if all the required data (listing fields) are fetched by the API call. 4. And then to validate each and every data and XML tags fetched by the API call (response) against the checkpoints (expected data/tags) available in the data sheet 5. And publish the results. (Results will be displayed in the terminal and also documented in a file ‘Test_Report’) (Note: All the input data and the expected data/tags are read from the data sheet by the script) | Inventory_getInventory.pyc | The data sheet ‘inv.csv’ can be manipulated and the script will show the results accordingly. | 16 | CASE: All the data specified in the data sheet are correct, and run the script EXPECTED: The script should perform the call and validate all the tags/data, and should publish the overall result as ‘PASSED’. Also the status code 200 should be displayed, Along with individual tag/data validation status as PASSED |  | Salaudeen
[8 empty] | 17 | CASE: Some of the field data specified in the data sheet are NOT correct, and run the script EXPECTED: The script should perform the call and validate all the tags/data, and should publish the overall result as ‘PASSED WITH ERROR / DATA MISMATCH’. Also the status code 200 should be displayed, along with the individual tag/data validation status like FAILED or PASSED |  | Salaudeen
[8 empty] | 18 | CASE: Username or password are not correct in the data sheet, and run the script EXPECTED: The scipt should perform the call, and should publish the overall result as ‘FAILED’, along with reason for failure ‘Security Error’ and the status code 500. |  | Salaudeen
[8 empty] | 19 | CASE: Endpoint is not correct in the data sheet, and run the script EXPECTED: The scipt should perform the call, and should publish the overall result as ‘FAILED’, along with reason for failure ‘No Service found. Your Endpoint could be wrong’ and the status code 404. |  | Salaudeen
[8 empty] | 20 | CASE: Remove one or some of the data columns in the data sheet, and run the script EXPECTED: The script should perform the call and validate all the tags/data, and should publish the overall result as ‘PASSED WITH ERROR / DATA MISMATCH’. Also the status code 200 should be displayed, A warning/failed message should be displayed stating that ‘MAY BE THE COLUMN/DATA ARE MISSING IN YOUR INPUT FILE. FILL THE REQUIRED TEST DATA AND TRY AGAIN..” Along with the other individual tag/data validation status as PASSED |  | Salaudeen
5 | InventoryAPI | GetSkuQuantity | Regression Script | inv.csv | 1. To insert a product into Listing table for any marketplace with all the required fields. 2. And to run the GetSkuQuantity call by reading the input data from the datasheet and to see if the call is success. 3. And to see if all the required data (listing fields) are fetched by the API call. 4. And then to validate each and every data and XML tags fetched by the API call (response) against the checkpoints (expected data/tags) available in the data sheet 5. And publish the results. (Results will be displayed in the terminal and also documented in a file ‘Test_Report’) (Note: All the input data and the expected data/tags are read from the data sheet by the script) | Inventory_getSkuQuantity.pyc | The data sheet ‘inv.csv’ can be manipulated and the script will show the results accordingly. | 16 | CASE: All the data specified in the data sheet are correct, and run the script EXPECTED: The script should perform the call and validate all the tags/data, and should publish the overall result as ‘PASSED’. Also the status code 200 should be displayed, Along with individual tag/data validation status as PASSED |  | Salaudeen
[8 empty] | 17 | CASE: Some of the field data specified in the data sheet are NOT correct, and run the script EXPECTED: The script should perform the call and validate all the tags/data, and should publish the overall result as ‘PASSED WITH ERROR / DATA MISMATCH’. Also the status code 200 should be displayed, along with the individual tag/data validation status like FAILED or PASSED |  | Salaudeen
[8 empty] | 18 | CASE: Username or password are not correct in the data sheet, and run the script EXPECTED: The scipt should perform the call, and should publish the overall result as ‘FAILED’, along with reason for failure ‘Security Error’ and the status code 500. |  | Salaudeen
[8 empty] | 19 | CASE: Endpoint is not correct in the data sheet, and run the script EXPECTED: The scipt should perform the call, and should publish the overall result as ‘FAILED’, along with reason for failure ‘No Service found. Your Endpoint could be wrong’ and the status code 404. |  | Salaudeen
[8 empty] | 20 | CASE: Remove one or some of the data columns in the data sheet, and run the script EXPECTED: The script should perform the call and validate all the tags/data, and should publish the overall result as ‘PASSED WITH ERROR / DATA MISMATCH’. Also the status code 200 should be displayed, A warning/failed message should be displayed stating that ‘MAY BE THE COLUMN/DATA ARE MISSING IN YOUR INPUT FILE. FILL THE REQUIRED TEST DATA AND TRY AGAIN..” Along with the other individual tag/data validation status as PASSED |  | Salaudeen